## Sheet2
Distinct Count of cellname | VENDOR
Suffix | HUAWEI | Grand Total
_FE | 66 | 66 | Row Labels | Count of cellname
Grand Total | 66 | 66 | 01.HN Passed - Done Delete Suffix | 1
|  |  | ISDP Milestone Blank - NY Swap & Integration | 16
|  |  | NY RFC | 37
|  |  | Reloc by 3rd party Indosat | 12
|  |  | Grand Total | 66

## Sheet1
DATE | Weekly | cellname | SITEID | SITE ID2 | VENDOR | New_Region | Circle | Suffix | PIC | Aging down | Administrative_status | Suffix Aging Class | Remark RO
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_D_1_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_D_2_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_D_3_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_D_4_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_G_1_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_G_2_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_G_3_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_G_1_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_G_2_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_G_3_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_G_1_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_G_2_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_G_3_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | ACTIVATED | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 12JKS0147_IN_APTPAKUSGNTR_L18_29_FE | 12JKS0147 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | 1 | CELL_ACTIVE | Aging < 15 Days | 01.HN Passed - Done Delete Suffix
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L18_11_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L18_12_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L18_13_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L18_14_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L18_21_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L18_22_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L18_23_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L18_24_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L21_11_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L21_12_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L21_21_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKS0693_IN_CYBER2_MC_L21_22_FE | 12JKS0693 | 12JKS | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | ISDP Milestone Blank - NY Swap & Integration
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L18_13_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L18_23_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L18_A12_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L18_A22_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L21_23_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L21_A22_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L9_1_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L9_2_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 12JKT0778_MESSWARA_PL_L9_3_FE | 12JKT0778 | 12JKT | HUAWEI | INNER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | Reloc by 3rd party Indosat
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L18_11_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L18_12_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L18_13_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L18_21_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L18_22_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L18_23_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L21_21_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L21_22_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L21_23_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L9_1_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L9_2_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13BGR0153_CIPARIGI_TB_L9_3_FE | 13BGR0153 | 13BGR | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L18_11_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L18_12_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L18_21_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L18_22_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L18_A13_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L18_A23_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L18_B13_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L18_B23_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L21_11_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L21_12_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L21_21_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L21_22_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L21_A13_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L21_A23_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L21_B13_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L21_B23_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L9_1_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L9_2_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC
2026-09-05 | W36 | 13CBN0426_KYMANISCIBDAK_L9_3_FE | 13CBN0426 | 13CBN | HUAWEI | OUTER JAKARTA | JAYA | _FE | Project | - | CELL_ACTIVE | Aging < 15 Days | NY RFC